# Farm Activities, Costs of Inputs and Labour: Production of Organic Pineapple

| Farm Activity |  | Date(s) | Costs of inputs |  |  |  |  | Family and hired labour |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Description and operator |  | Input | Unit | Quantity | Price per unit (GH¢) | Amount (GH¢) |  | Unit | Quantity | Value per unit (GH¢) | Amount (GH¢) |
| 1. | Cutting of trees and stumping | 16 weeks before planting |  |  |  |  |  | Hired Labour or Services | Contract | 1 | 200 | 200 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 2. | Clearing | 16 weeks before planting |  |  |  |  |  | Hired Labour or Services | Contract | 1 | 200 | 200 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 3. | 1st Ploughing with tractor (At least 30 cm deep!) | 15 weeks before planting |  |  |  |  |  | Hired Labour or Services | Contract | 1 | 45 | 45 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 4. | Sowing of cover crops | 12 weeks before planting | Mucuna seeds | 50 kg bag | 1 | 100 | 100 | Hired Labour or Services | PD | 5 | 4 | 20 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 5. | Incorporate cover crops (2nd ploughing) (at least 30 cm deep!) | 3 weeks before planting |  |  |  |  |  | Hired Labour or Services | Contract | 1 | 45 | 45 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 6. | Organic solid fertilizer application (Apply on wet ridges!) | 2 weeks before planting | Go Green (organic fertilizer) | 25 kg bag | 60 | 14 | 840 | Hired Labour or Services | PD | 5 | 4 | 20 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 7. | Harrowing | 2 weeks before planting |  |  |  |  |  | Hired Labour or Services | Contract | 1 | 30 | 30 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 8. | Ridging | 2 weeks before planting |  |  |  |  |  | Hired Labour or Services | Contract | 1 | 45 | 45 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 9. | Plastic mulching (Wait 2 weeks before planting!) | 2 weeks before planting | Plastic mulch | Roll | 3 | 140 | 420 | Hired Labour or Services | Contract | 1 | 120 | 120 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 10. | Sucker picking and removing of basal leaves and roots (let the suckers dry upside down for 10 days - at least 5 days of sun) | 2 weeks before planting | Suckers |  | 26,000 |  | Own production | Hired Labour or Services | PD | 12 | 4 | 48 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 11. | Sucker collection | 3 days before planting |  |  |  |  |  | Hired Labour or Services | PD | 12 | 4 | 48 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 12. | Sorting and grading of suckers | 2 days before planting |  |  |  |  |  | Hired Labour or Services | PD | 4 | 4 | 16 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 13. | Sucker treatment (dip in mixture of 200 ltr. of water with Fundamental Sulphur and Citric Acid) | 1 day before planting | Fundamental Sulphur Citric Acid | kg | 4 | 6 | 24 | Hired Labour or Services | PD | 4 | 4 | 16 |
|  |  |  |  | Ltr. | 0.2 | 15 | 3 | Family Labour | Person-days |  |  |  |
| 14. | Mark holes with rope and plant per grade! (26,000 per acre) | Day 0 |  |  |  |  |  | Hired Labour or Services | Contract | 1 | 120 | 120 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 15. | Counting the number of plants | Day 1 |  |  |  |  |  | Hired Labour or Services | PD | 2 | 4 | 8 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 16. | Neem extract application (100 ml for 200 ltr of water) | Day 3 | Neem Extract | Ltr. | 0.6 | 4 | 2.4 | Hired Labour or Services | PD | 6 | 4 | 24 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 17. | Weeding (manually with a hoe!) | Day 7 Day 30 Day 45 |  |  |  |  |  | Hired Labour or Services | PD | 6 | 4 | 24 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 18. | Weeding (manually with a hoe!) | Day 60 Day 75 Day 90 |  |  |  |  |  | Hired Labour or Services | PD | 6 | 4 | 24 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| Farm Activity |  | Date(s) | Costs of inputs |  |  |  |  | Family and hired labour |  |  |  |  |
| No. | Description and operator |  | Input | Unit | Quantity | Price per unit (GH¢) | Amount (GH¢) |  | Unit | Quantity | Value per unit (GH¢) | Amount (GH¢) |
| 19. | Leaves check: Weighing of D-Leaves | Day 91 |  |  |  |  |  | Hired Labour or Services |  |  |  |  |
|  |  |  |  |  |  |  |  | Family Labour | Person-days | 1 | 4 | 4 |
| 20. | Weeding (manually with a hoe!) | Day 105 Day 120 |  |  |  |  |  | Hired Labour or Services | PD | 4 | 4 | 16 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 21. | Leaves check: Weighing of D-Leaves | Day 121 |  |  |  |  |  | Hired Labour or Services |  |  |  |  |
|  |  |  |  |  |  |  |  | Family Labour | Person-days | 1 | 4 | 4 |
| 22. | Neem extract application (100 ml for 200 ltr of water) | Day 122 | Neem Extract | Ltr. | 0.6 | 4 | 2.4 | Hired Labour or Services | PD | 6 | 4 | 24 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 23. | Foliar fertilizer spraying (1 ltr for 200 ltr. of water) | Day 130 | Fontana (NPK + micro elements) | Ltr. | 6.4 | 1 | 6.4 | Hired Labour or Services | PD | 6 | 4 | 24 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 24. | Weeding (manually with a hoe!) | Day 135 Day 150 |  |  |  |  |  | Hired Labour or Services | PD | 4 | 4 | 16 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 25. | Leaves check: Weighing of D-Leaves | Day 151 |  |  |  |  |  | Hired Labour or Services |  |  |  |  |
|  |  |  |  |  |  |  |  | Family Labour | Person-days | 1 | 4 | 4 |
| 26. | Weeding (manually with a hoe!) | Day 165 Day 180 |  |  |  |  |  | Hired Labour or Services | PD | 2 | 4 | 8 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 27. | Leaves check: Weighing of D-Leaves | Day 181 |  |  |  |  |  | Hired Labour or Services |  |  |  |  |
|  |  |  |  |  |  |  |  | Family Labour | Person-days | 1 | 4 | 4 |
| 28. | Counting the number of plants | Day 182 |  |  |  |  |  | Hired Labour or Services | PD | 2 | 4 | 8 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 29. | Weeding (manually with a hoe!) | Day 195 Day 210 |  |  |  |  |  | Hired Labour or Services | PD | 2 | 4 | 8 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 30. | Leaves check: Weighing of D-Leaves | Day 211 |  |  |  |  |  | Hired Labour or Services |  |  |  |  |
|  |  |  |  |  |  |  |  | Family Labour | Person-days | 1 | 4 | 4 |
| 31. | Foliar fertilizer spraying (1 ltr for 200 ltr. of water) | Day 212 | Fontana (NPK + micro elements) | Ltr. | 6.4 | 1 | 6.4 | Hired Labour or Services | PD | 6 | 4 | 24 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 32. | Weeding (manually with a hoe!) | Day 225 |  |  |  |  |  | Hired Labour or Services | PD | 1 | 4 | 4 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 33. | Counting the number of plants | Day 235 |  |  |  |  |  | Hired Labour or Services | PD | 2 | 4 | 8 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 34. | Weeding (manually with a hoe!) | Day 240 |  |  |  |  |  | Hired Labour or Services | PD | 1 | 4 | 4 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 35. | Leaves check: Weighing of D-Leaves | Day 241 |  |  |  |  |  | Hired Labour or Services |  |  |  |  |
|  |  |  |  |  |  |  |  | Family Labour | Person-days | 1 | 4 | 4 |
| 36. | Forcing (1st time) When D-leaves average over 80g | Day 242 | Ethylene Charcoal | kg | 0.4 | 120 | 48 | Hired Labour or Services | PD | 12 | 4 | 48 |
|  |  |  |  | 25 kg bag | 0.12 | 6 | 0.72 | Family Labour | Person-days |  |  |  |
| 37. | Forcing (2nd time) | Day 243 | Ethylene Charcoal | kg | 0.4 | 120 | 48 | Hired Labour or Services | PD | 12 | 4 | 48 |
|  |  |  |  | 25 kg bag | 0.12 | 6 | 0.72 | Family Labour | Person-days |  |  |  |

| Farm Activity |  | Date(s) | Costs of inputs |  |  |  |  | Family and hired labour |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Description and operator |  | Input | Unit | Quantity | Price per unit (GH¢) | Amount (GH¢) |  | Unit | Quantity | Value per unit (GH¢) | Amount (GH¢) |
| 38. | Counting the number of plants | Day 244 |  |  |  |  |  | Hired Labour or Services | PD | 2 | 4 | 8 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 39. | Weeding (manually with a hoe!) | Day 255 Day 270 Day 285 Day 300 |  |  |  |  |  | Hired Labour or Services | PD | 4 | 4 | 16 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 40. | Weeding (manually with a hoe!) | Day 315 Day 330 Day 345 Day 360 |  |  |  |  |  | Hired Labour or Services | PD | 4 | 4 | 16 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 41. | Neem extract application (100 ml for 200 ltr of water) | Day 361 | Neem Extract | Ltr. | 0.3 | 4 | 1.2 | Hired Labour or Services | PD | 6 | 4 | 24 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 42. | Check the Brix (with refractometer) and the maturity (Start to check maturity 130 days after forcing and then every day!) | Day 370 Day 371 Day 372 Day 373 Day 374 Day 375 Day 376 Day 377 Day 378 Day 379 Day 380 |  |  |  |  |  | Hired Labour or Services | PD | 4 | 4 | 16 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 43. | Harvesting | Day 380 |  |  |  |  |  | Hired Labour or Services | PD | 40 | 4 | 160 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 44. | Transport to packhouse | Day 380 |  |  |  |  |  | Hired Labour or Services | Contract | 1 | 240 | 240 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |
| 45. | Cut the peduncle and dip it in mixture of 200 Ltr. of water with Fundamental Sulphur and Citric Acid | Day 380 | Fundamental Sulphur Citric Acid | kg | 0.3 | 6 | 1.8 | Hired Labour or Services | PD | 8 | 4 | 32 |
|  |  |  |  | Ltr. | 0.1 | 15 | 1.5 | Family Labour | Person-days |  |  |  |
| 46. | Grading, packing in boxes, packing pallets, labelling, quality control | Day 380 | Boxes | Box | 1800 | 2.6 | 4680 | Hired Labour or Services | PD | 40 | 4 | 160 |
|  |  |  | Wooden pallets | Pallet | 26 | 14 | 364 | Family Labour | Person-days |  |  |  |
|  |  |  | Strapping rolls | Roll | 2 | 50 | 100 | Hired Labour or Services |  |  |  |  |
|  |  |  | Strapping pins | Pack | 1 | 30 | 30 | Family Labour | Person-days |  |  |  |
| 47. | Transport to port for shipment | Day 380 |  |  |  |  |  | Hired Labour or Services | Contract | 1 | 1 200 | 1 200 |
|  |  |  |  |  |  |  |  | Family Labour | Person-days |  |  |  |

|  |  |  |  |  |  | Total Inputs (GH¢): | 6 680 | Hired Labour or Services | Total (PD): | - | Total (GH¢): | 3 173 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 PD (Person-day) = 5 hours of work |  |  |  |  |  | Family Labour | Total (PD): | - | Total (GH¢): | 24 |